## Implementation Plan
GPS INSIGHT HOS IMPLEMENTATION PLAN |  |  |  | Customer Name:
Start Date:
End Date:
Status | 1. Contract & Account Creation | Due Date | Date Scheduled | Date Completed | Tools | Resources
a. Contract & Setup
| Contract Execution Date: |  |  |  |  | Sales
| Implementation Deadline Date: |  |  |  |  | Sales
| Total Device Count: |  |  |  |  | Sales
| Sales and Account Manager to review ELD Support Tools in KB to prepare for HOS of Implementation. |  |  |  | https://kb.gpsinsight.com/eld-support-tools/ | Sales, Account Manager
| Sales to send the customer the "HOS Customer Worksheet" provide the information needed for customer account setup. |  |  |  | https://help.gpsinsight.com/best-practice/hos-customer-worksheet/ | Sales
| Customer to send the completed "HOS Customer Worksheet" back to Sales. |  |  |  |  | Customer
| Sales to Initiate GPS Insight/HOS account setup in NS. See "Linked Account Setup" in KB. |  |  |  | https://kb.gpsinsight.com/linked-account-setup/ | Sales
| Support to send HOS request for ISE account association in NS, and complete final account setup. See "ISE Account Association" and "Internal Account Setup" in KB. |  |  |  | https://kb.gpsinsight.com/eld-support-tools/ | Support
| Sales and Account Manager will receive verification HOS Request Status is "Completed" from GPSI Support. |  |  |  |  | Sales
| Account Manager to verify HOS functionality is accessible through portal on Admin Account. Click "More" tab and verify following menu items listed: 1. Hours of Service 2. HOS Driving Availability 3. Driver-Vehicle Inspection Report 4. Confirm ELD Filter is available on Manage Vehicles Page (If HOS functionality not available through GPSI Portal, Account Manager to make available through Account> Manage users>Menu-access>Custom then click the Hours of Service, HOS Driving, Driver-Vehicle Report for specific Users.) |  |  |  |  | Account Manager
| Account Manager to provide implementation plan to customer if needed. Determine if any other documents are required. |  |  |  |  | Account Manager
Status | 2. Project Initiation | Due Date | Date Scheduled | Date Completed | Tools | Resources
| Contract Execution should be complete. |  |  |  |  | Sales, Customer
| Kick-off email sent to Customer with links to Implementation plan, HOS Help, vehicle list and training. |  |  |  | https://help.gpsinsight.com/docs/about-hours-of-service/ | Account Manager
| Kick-off call with the Customer and Account Manager. Customer identifies key contacts and provides contact information: Fleet Project Manager, Installation Manager, Department contacts, Fleet manager(s), Training Coordinator, etc. |  |  |  |  | Customer, Sales, Account Manager
| Account Manager to provide an overview of GPSI Account Management and our role to Customer Fleet Project Manager. GPSI can provide the tools to manage fleet compliance to the ELD Mandate but the customer is ultimately responsible for that management of their HOS program and compliance. |  |  |  |  | Account Manager, Customer
| Account Manager to discuss and review implementation schedule with Fleet Project Manager. Gain understanding on any time constraints. |  |  |  |  | Account Manager, Customer
| Account Manager/Sales to send customer Vehicle List and provide overview of required information. |  |  |  |  | Account Manager
| Account Manager to send customer User, Driver, and Location templates outlining the information the customer needs to add into the GPSI HOS Application. Include column with user credentials including whether a driver or user or both. |  |  |  |  | Account Manager
| Customer to determine order of department implementation and notify Account Manager. |  |  |  |  | Account Manager, Customer
a. Account Set Up Overview
| Customer to define contacts in each department for account set up and the Fleet manager in each Department. Customer is responsible for pulling in and coordinating with department contacts for training/account set up as needed. |  |  |  |  | Account Manager, Customer
| Account Set Up Overview (Detailed information in Section 6): 1. Account created in NS by Sales and setup requested and linked by Support 2. Installation of GPSI-4000 and Verification by GPSI Support which will add the vehicle to the GPSI Portal 3. Installation of ELD Tablet and Verification that includes Provisioning of tablet by GPSI Support which will add the vehicle into GPSI HOS Portal 4. Add Home Terminals, User Roles, Users, Drivers, etc. 5. Configure/customize DVIR Inspection Checklist 6. Link Drivers in the GPSI Portal (GPSI Driver Ref ID matched to HOS Driver ID) 7. Link Vehicles in the GPSI Portal (Match HOS vehicle ID with Device label) 7. Create HOS/DVIR Dashboard in GPSI Portal and configure Dashlets |  |  |  |  | Account Manager
| Review Help Center Resources for Account setup, Support, Training etc. Request whoever is responsible for setting up the account take HOS Training Courses. |  |  |  | https://help.gpsinsight.com/training-courses/ | Account Manager, Customer
b. Installation Overview
| Installation Meeting for Account Manager, GPSI Installation Coordinator and Customer Fleet Project Manager to set installation expectations, discuss vehicle availability, special wiring/mounting instructions, PPEs, site restrictions/access, and identify installation deployment type (assembly line, staged vehicles, etc.), vehicle keys. |  |  |  |  | Account Manager, Customer, Install Coordinator
| Provide an overview of the installation process: 1. Devices shipped to install location 2. Packing/assembly specifics 3. Installation of GPSI-4000 and ELD-2000 Tablet connected 4. Installation verification 5. ELD Tablet Provisioning 6. Vehicle registration (Installs must be called in to GPSI Support) Recommend install is performed during GPSI Support business hours 5 AM-6 PM. If not during normal hours, GPSI Support Manager must be notified to ensure proper coverage. |  |  |  |  | Account Manager
| Customer are strongly recommended to test drive all vehicles immediately following installation to verify odometer and speed data is populating correctly in the HOS application. |  |  |  | https://kb.gpsinsight.com/eld-support-tools/#ipt_kb_toc_11527_6 | Customer
| Determine which type of installation will be performed: 1. Third party installer - GPSI Coordinated 2. Self-Install |  |  |  |  | Account Manager, Customer
| We ship everything FedEx 2 day by default. Verify that is acceptable to customer. |  |  |  |  | Account Manager
| Discuss post installation Device Maintenance program requirements and provide recommendations regarding GPSI tools, processes, and invoicing. |  |  |  |  | Account Manager, Customer
This section applies to Self-Install Only:
| If self-install is chosen, Account Manager sends install guides/video links to Customer. Account Manager verifies Customer has viewed video/materials and is comfortable performing the installation. If not, Account Manager schedules call with Customer, and Installation team adds any clarity that is needed. |  |  |  |  | Account Manager, Customer
| Customer signs off on Self-Install Terms and Conditions. |  |  |  |  | Customer
| Account Manager sends Vehicle List template to Customer. |  |  |  |  | Account Manager
| Customer provides Vehicle List to Account Manager include (per vehicle) the following: Vehicle Label, VIN #, Year, Make, Model, Department, Add ons: (PTO, Driver ID), Install Location address/contact info, Full Ship to Address/contact info. |  |  |  |  | Customer
| GPSI Installs assess Vehicle List and provides device recommendations. |  |  |  |  | Account Manager, Install Coordinator
| If applicable, GPSI Installs provides recommendations on unit type/installation method to Account Manager for Customer. |  |  |  |  | Install Coordinator
| Warranty requires that install verification is performed after each installation by calling 866-477-4321 x2 while the installer is at the vehicle. Registration will be handled by GPSI Support at that time. ELD-2000 Tablet is under warrantee for 1 year. |  |  |  |  | Installer, Support
| Additional MDT Provisioning and verification of odometer and speed data is required for HOS/ELD. See "Installation Verification: ELD-2000" steps in KB. |  |  |  | https://kb.gpsinsight.com/eld-support-tools/#ipt_kb_toc_11527_6 | Installer, Support
c. Integration Overview
| Integration functionality will increase as the GPSI HOS evolves and those updates will be communicated to the Customer. |  |  |  |  | Account Manager
Status | 3. Pre-Order (Applies to Paid Install Only) | Due Date | Date Scheduled | Date Completed | Tools | Resources
| Account Manager sends Vehicle List template to Customer. |  |  |  |  | Account Manager
| Customer emails Installs a vetted vehicle list to include (per vehicle) the following: Vehicle Label, VIN #, Year, Make, Model, Department, Install Address, Install Contact info (Name, Phone Number, Email Address), Full Ship to Address and Ship to Contact Info (Name, Phone Number, Email Address). |  |  |  |  | Customer
| It is recommended that Sales uses the KB Tool "Find a Device" to determine appropriate device type, cables and add-ons based on vehicle year/make/model to create Order. Sales sends the completed Vehicle List to Installs/Sales Engineer for review. Certain vehicles, such as 16 Pin Mack Trucks require special cables. |  |  |  |  | Sales, Install Coordinator
| GPSI Installs reviews vehicle list and provides feedback on unit type/equipment for Order to GPSI Sales. |  |  |  |  | Install Coordinator
| Vehicle List Spreadsheet provided to Customer outlining vehicle devices, accessory cable requirements and assignments for Installation. a. In professional installation scenario Sales creates a Sales Admin Installation Request form and verifies it referencing Vehicle List Spreadsheet. b. In self-installation scenarios, Sales would send Vehicle List to Customer Project Manager to provide to installers to refer to during installation. |  |  |  |  | Install Coordinator, Sales
| When multiple drivers will be driving one vehicle, Driver Training should begin immediately, please start Section 8 b of Implementation plan. Customer HOS Manager then conducts Driver training and instructs Drivers to complete the online HOS Driver test. After all Drivers pass the test the Tablet is plugged in. Please see below for the 2 scenarios: 1. All Drivers are trained and pass test prior to install: Installers will verify install and plug ELD tablets in. 2. All Drivers are not trained at time of install: All tablets will not be plugged in until all Drivers are trained. The Driver will then plug in the Tablet once trained. |  |  |  | https://help.gpsinsight.com/best-practice/promoting-driver-adoption-of-gps-tracking/ | Customer HOS Manager, Drivers
| Customer Accounting begins process to create the two POs; by Department one for Installation and Hardware and another for Service. |  |  |  |  | Customer
| Installs updates the spreadsheet with the two POs for every vehicle and emails the updated spreadsheet to GPSI Sales for Sales Order creation purposes. *Units will not ship without both POs* |  |  |  |  | Install Coordinator
Status | 4. Order | Due Date | Date Scheduled | Date Completed | Tools | Resources
| GPSI Sales creates Estimate for device orders. This is sent to customer for approval. |  |  |  |  | Sales
| Customer approves Estimate. |  |  |  |  | Customer
| Account Manager sends "Welcome Email" to Customer via Clearslide templates which includes links to resources and training. |  |  |  |  | Account Manager
| GPSI Installer creates installation route with installation dates and times; first install date will be 1.5-2 weeks from this day if possible |  |  |  |  | Installer
| GPSI Installer emails updated spreadsheet with install site scheduled dates and times to Customer and Installs. |  |  |  |  | Installer
| Customer emails spreadsheet to all site contacts to make them aware of their upcoming appointments. Any install changes must be handled internally by Customer and authorized by GPSI Installer; to include moving of hardware from one location to another. |  |  |  |  | Customer
| Vehicle List with device/cable requirements sent to Fulfillment for printing and inclusion in box. |  |  |  |  | Sales
| GPSI Fulfillment begins shipping orders via standard FedEx 2 Day Air. |  |  |  |  | Fulfillment
Status | 5. Installation | Due Date | Date Scheduled | Date Completed | Tools | Resources
Preparation for GPSI Install
| One to two business days prior to each schedule locations appointment the Preferred installation vendor will reach out to the site contact in the spreadsheet to remind them of the schedule appointment, number of techs arriving, and number of vehicles they expect to touch per day while they’re onsite. |  |  |  |  | Installer, Customer
| Preferred installation vendor installs, verifies and registers devices. If needed, GPSI Tech Support will also be available to verify and register devices. |  |  |  |  | Installer
| If a vehicle does not arrive to a scheduled appointment Preferred installation vendor will email Account Manager, Installation Coordinator, key customer personal involved (Customer Deployment Project Manager) asking customer if the vehicle can be traveled to the next install location in the technicians route. |  |  |  |  | Installer
| If the vehicle cannot be made available, the vehicle will be flagged for follow-up and after completion of the initial roll-out all follow-up vehicles will be combined and placed into a new spreadsheet which is then sent to the key customer personal involved (Customer Deployment Project Manager) for updated install location and site contact information. |  |  |  |  | Install Coordinator
Installation Begins
| Installer registers the installed vehicles in the GPS Insight Portal. (Vehicles may take up to 24 hours to be viewed in GPS Insight system.) |  |  |  |  | Installer
| Installer contacts GPSI Support (either via the mobile app or call in) at the time of install to verify the Installation. |  |  |  |  | Installer
| Installer installs and connects the ELD-2000 Tablet to the GPSI-4000 device. |  |  |  |  | Installer
| Installer contacts GPSI Support to Provision the Tablet at time of install so it will be available in the GPSI HOS Portal. See "Installation Verification: ELD-2000" steps in KB. |  |  |  |  | Installers, Support
| If multiple Drivers will be driving one vehicle and Drivers have not been trained the Installer will then disconnect Tablet. If only one Driver will be driving a vehicle the Installer will leave the Tablet plugged in. Every Driver should be instructed to plug the tablet in once they are trained and enter the vehicle (if it is unplugged). Please see Driver Training section 8b. |  |  |  |  | Customer
Installation Verification
| GPSI Support verifies device reporting across the entire fleet. GPSI Account Manager to request this. |  |  |  |  | Account Manager, Support
| GPSI Support verifies ELD reporting across the entire fleet. Verify driving events are being reported by every ELD Tablet. GPSI Account Manager to Request this. |  |  |  |  | Account Manager, Support
| Install Coordinator audits installation and identifies any remaining items to be accomplished (e.g., total installed vs. vehicle list, units not installed, vehicles unavailable) and communicates to Customer. |  |  |  |  | Install Coordinator
| Install Coordinator begins coordinating any follow up installation work required. |  |  |  |  | Install Coordinator
Device Maintenance
| Once GPS devices are installed there is maintenance that is required on the Customer's part to verify device performance. This includes identifying potential device and tablet issues and arranging for service to vehicles for troubleshooting and repair. There are tools available within the GPS Insight Application that customers should use to proactively manage their fleet and devices. We recommend the Customer Fleet Manager, and whomever else is responsible for ensuring the vehicle are running and devices are working correctly, be notified should a vehicle or device need attention. Please see below for the tools we recommend Customers should use and details regarding each. |  |  |  |  | Account Manager, Customer
| Account Manager to send post installation Device Maintenance Program to Customer. Review program and provide recommendations regarding GPSI tools, processes, and invoicing. |  |  |  |  | Account Manager, Customer
Installation Complete
| Install Coordinator communicates to Customer and Account Manager that installation is complete |  |  |  |  | Install Coordinator
Status | 6. Account Set Up | Due Date | Date Scheduled | Date Completed | Tools | Resources
Kick-Off Meeting
| Discuss and review implementation recommended process. Some of the account set up can be performed prior to vehicles and tablets being added to the account. Please follow the order listed below: a. Home Screen Overview b. Settings c. Home Terminal d. Organizational Details e. User Roles f. Drivers & Driver Groups g. Users h. Devices i. Assets & Asset Groups (optional) j. Locations (optional) k. DVIR l. HOS Reports in GPSI Hours of Service Portal m. HOS in GPSI Fleet Tracking Portal |  |  |  | GPSI Portal> More> Hours of Service > Open | Account Manager, Customer
a. HOS Home Screen Overview
Overview: Explore the HOS pages which contain settings, management tools and reports to track/demonstrate compliance. To access from GPSI Portal select More>Hours of Service>Open. | Note: Hierarchy Vehicle Groups is an advanced way to organize vehicles and requires set up assistance. It is to be used for the organization of vehicles for fleets over 100 that have sophisticated needs. This includes using API's to move vehicles, custom report groups, scheduled report/alerts distribution lists, and escalating alerts. Note: The majority mid-market and small business Customers will be satisfied using Vehicle Groups. Customers utilizing Hierarchy may also occasionally use Vehicle groups, because they are quick to set up, for specific needs like wanting to see unrelated vehicles grouped together. |  | Note: Hierarchy Vehicle Groups is an advanced way to organize vehicles and requires set up assistance. It is to be used for the organization of vehicles for fleets over 100 that have sophisticated needs. This includes using API's to move vehicles, custom report groups, scheduled report/alerts distribution lists, and escalating alerts. Note: The majority mid-market and small business Customers will be satisfied using Vehicle Groups. Customers utilizing Hierarchy may also occasionally use Vehicle groups, because they are quick to set up, for specific needs like wanting to see unrelated vehicles grouped together. | Note: Hierarchy Vehicle Groups is an advanced way to organize vehicles and requires set up assistance. It is to be used for the organization of vehicles for fleets over 100 that have sophisticated needs. This includes using API's to move vehicles, custom report groups, scheduled report/alerts distribution lists, and escalating alerts. Note: The majority mid-market and small business Customers will be satisfied using Vehicle Groups. Customers utilizing Hierarchy may also occasionally use Vehicle groups, because they are quick to set up, for specific needs like wanting to see unrelated vehicles grouped together. | Note: Hierarchy Vehicle Groups is an advanced way to organize vehicles and requires set up assistance. It is to be used for the organization of vehicles for fleets over 100 that have sophisticated needs. This includes using API's to move vehicles, custom report groups, scheduled report/alerts distribution lists, and escalating alerts. Note: The majority mid-market and small business Customers will be satisfied using Vehicle Groups. Customers utilizing Hierarchy may also occasionally use Vehicle groups, because they are quick to set up, for specific needs like wanting to see unrelated vehicles grouped together. | Note: Hierarchy Vehicle Groups is an advanced way to organize vehicles and requires set up assistance. It is to be used for the organization of vehicles for fleets over 100 that have sophisticated needs. This includes using API's to move vehicles, custom report groups, scheduled report/alerts distribution lists, and escalating alerts. Note: The majority mid-market and small business Customers will be satisfied using Vehicle Groups. Customers utilizing Hierarchy may also occasionally use Vehicle groups, because they are quick to set up, for specific needs like wanting to see unrelated vehicles grouped together.
| Home - Takes Customer back to the Home screen. By default, the Home screen displays the Driver Log Conflicts Summary. |  |  |  | https://help.gpsinsight.com/docs/about-hours-of-service/administrator-reference/exploring-the-hos-admin-interface/ | Account Manager, Customer
| HOS - Contains various reports required to demonstrate compliance. |  |  |  |  | Account Manager, Customer
| DVIR - Contains management tools and reports related to vehicles, trailers, and other company assets related to HOS. |  |  |  |  | Account Manager, Customer
| Setup - Allows Customer to enter initial setup information related to drivers, assets, and locations. |  |  |  |  | Account Manager, Customer
| Admin - Allows Customer to configure portal options for Customer account. |  |  |  |  | Account Manager, Customer
| Settings - Allows Customer to configure Customer user preferences, such as time zone. |  |  |  |  | Account Manager, Customer
| Help - Provides a comprehensive Help resource for all configuration options, settings, reports, and terminology used in the portal. |  |  |  |  | Account Manager, Customer
b. Settings
Overview: Allows Customer to configure Customer user preferences, such as time zone. | Note: Hierarchy Vehicle Groups is an advanced way to organize vehicles and requires set up assistance. It is to be used for the organization of vehicles for fleets over 100 that have sophisticated needs. This includes using API's to move vehicles, custom report groups, scheduled report/alerts distribution lists, and escalating alerts. Note: The majority mid-market and small business Customers will be satisfied using Vehicle Groups. Customers utilizing Hierarchy may also occasionally use Vehicle groups, because they are quick to set up, for specific needs like wanting to see unrelated vehicles grouped together. |  | Note: Hierarchy Vehicle Groups is an advanced way to organize vehicles and requires set up assistance. It is to be used for the organization of vehicles for fleets over 100 that have sophisticated needs. This includes using API's to move vehicles, custom report groups, scheduled report/alerts distribution lists, and escalating alerts. Note: The majority mid-market and small business Customers will be satisfied using Vehicle Groups. Customers utilizing Hierarchy may also occasionally use Vehicle groups, because they are quick to set up, for specific needs like wanting to see unrelated vehicles grouped together. | Note: Hierarchy Vehicle Groups is an advanced way to organize vehicles and requires set up assistance. It is to be used for the organization of vehicles for fleets over 100 that have sophisticated needs. This includes using API's to move vehicles, custom report groups, scheduled report/alerts distribution lists, and escalating alerts. Note: The majority mid-market and small business Customers will be satisfied using Vehicle Groups. Customers utilizing Hierarchy may also occasionally use Vehicle groups, because they are quick to set up, for specific needs like wanting to see unrelated vehicles grouped together. | Note: Hierarchy Vehicle Groups is an advanced way to organize vehicles and requires set up assistance. It is to be used for the organization of vehicles for fleets over 100 that have sophisticated needs. This includes using API's to move vehicles, custom report groups, scheduled report/alerts distribution lists, and escalating alerts. Note: The majority mid-market and small business Customers will be satisfied using Vehicle Groups. Customers utilizing Hierarchy may also occasionally use Vehicle groups, because they are quick to set up, for specific needs like wanting to see unrelated vehicles grouped together. | Note: Hierarchy Vehicle Groups is an advanced way to organize vehicles and requires set up assistance. It is to be used for the organization of vehicles for fleets over 100 that have sophisticated needs. This includes using API's to move vehicles, custom report groups, scheduled report/alerts distribution lists, and escalating alerts. Note: The majority mid-market and small business Customers will be satisfied using Vehicle Groups. Customers utilizing Hierarchy may also occasionally use Vehicle groups, because they are quick to set up, for specific needs like wanting to see unrelated vehicles grouped together.
| Account Manager to provide training on Settings to Customer. See training topics below. |  |  |  | https://help.gpsinsight.com/docs/about-hours-of-service/administrator-reference/hos-admin-setup-tasks/ | Account Manager
| Customer to set Time zone and select whether or not to Adjust for DST. |  |  |  |  | Customer
| Customer to set defaults for other Setting options. |  |  |  |  | Customer
c. Home Terminal
Overview: A driver’s home terminal, or domicile, is the terminal from which the driver is dispatched and to which the driver returns with the most frequency. The home terminal is also the means by which a particular time zone is associated with a driver log. Home terminals control what records a driver or non-driver user may access via the web application, and they also allow Customer to filter records within the application.
| Provide training on Home Terminal to Customer. See training topics below. |  |  |  | https://help.gpsinsight.com/docs/about-hours-of-service/administrator-reference/hos-admin-setup-tasks/ | Account Manager, Customer
| Editing existing Home Terminal. The Time Zone being entered correctly is critical, this is regulatory. |  |  |  |  | Customer
| Add a new Home Terminal as needed. Review adding Manually and via Import. |  |  |  |  | Customer
d. Organizational Detail
Overview: Company information is managed here, in addition to data exchange and HOS duty status thresholds.
| Provide training and an overview of Organizational Detail. See training topics below. |  |  |  | https://help.gpsinsight.com/docs/about-hours-of-service/administrator-reference/hos-admin-setup-tasks/ | Account Manager, Customer
| Edit Organizational Information. This is prepopulated via NS. |  |  |  |  | Customer
| Select Applications. HOS and DVIR should both be checked. Do not uncheck. |  |  |  |  | Customer
| Edit General Tab (Data Exchange settings). Defaults recommended. |  |  |  |  | Customer
| Edit Hours of Service as needed. Do not edit "Vehicle in Motion" and "Vehicle Stopped" Thresholds as the defaults align with ELD Mandate. The other fields should be configured by Customer in line with their business. |  |  |  |  | Customer
e. User Roles
Overview: A user role is a collection of permissions to one or more web application features. There are two classes of user roles: System or Custom.
| Provide training and overview on User Roles to Customer. |  |  |  | https://help.gpsinsight.com/docs/about-hours-of-service/administrator-reference/hos-admin-setup-tasks/ | Account Manager, Customer
| Edit a system User Role. |  |  |  |  | Customer
| Add a new custom User Role. |  |  |  |  | Customer
f. Drivers & Driver Groups
Overview: A driver is a person employed by a motor carrier who operates commercial motor vehicles as part of his or her duties. Create and Manage Driver IDs in both GPS and HOS Portals. They should match exactly or be associated to one another. Customer can alternatively create HOS driver profiles from within the GPS portal user interface. Customer can also use that interface to fix any broken associations between HOS driver profiles and GPS driver profiles.
| Provide training and overview on Drivers. See training topics below. |  |  |  | https://help.gpsinsight.com/docs/about-hours-of-service/administrator-reference/hos-admin-setup-tasks/ | Account Manager, Customer
| Account Manager to send links to Customer regarding Driver Adoption Best Practices. |  |  |  | https://help.gpsinsight.com/best-practice/promoting-driver-adoption-of-gps-tracking/
| Please see Driver Training section for recommended training which needs to occur to ensure correct adoption of ELD program. |  |  |  | https://help.gpsinsight.com/best-practice/promoting-driver-adoption-of-gps-tracking/ | Customer
| Account Manager will provide a spreadsheet of required Driver information to Customer. |  |  |  |  | Account Manager
| Add a new Driver manually. The Driver ID must be unique, exact and correct as it cannot be edited once the duty status has been submitted (the driver has signed in). |  |  |  |  | Customer
| Add new Drivers via import. |  |  |  |  | Customer
| Assign the following permissions: 1. Web Access: If Customer want the Driver to be able to log in to the portal be sure to check "Permit Web Access." 2. User Role: Select User Role. Drivers can also be added as users at this point. 3. Home Terminal Access: Assign Home Terminal. |  |  |  |  | Customer
| Provide training and overview on Driver Groups. Enables filtering and viewing by Driver Group but Home Terminals may also serve the same purpose. |  |  |  |  | Customer
| Verify Drivers were auto linked through the Driver Ref ID in GPSI Portal. |  |  |  |  | Customer
g. Users
Overview: Users can be added to provide individuals with web access to the HOS Admin portal. If that user is going to also be a Driver they should be added as a Driver first as that provides the option to also add them as a user. Once Customer create a user profile, the user type can’t change. If an existing user now requires access the mobile application and Driver Portal feature, Customer must add a separate driver profile for the person to use for this purpose.
| GPSI will provide Customer with an overview of Users. |  |  |  | https://help.gpsinsight.com/docs/about-hours-of-service/administrator-reference/hos-admin-setup-tasks/ | Account Manager, Customer
| Account Manager will provide a spreadsheet of required User information to Customer. |  |  |  |  | Account Manager
| Customer will determine the User roles each User will be assigned. |  |  |  |  | Customer
| Create new user. |  |  |  |  | Customer
| Add HOS functionality Menu-Access for specific Users through GPSI Portal by going to Account> Manage users>Menu-access>Custom then click boxes for Hours of Service, HOS Driving, Driver-Vehicle Report. |  |  |  |  | Customer
| Customer must send a welcome email with log in information to all users who have been added into the HOS Portal. Recommend all Users bookmark HOS portal for future access. |  |  |  |  | Customer
| Assign DVIR Access settings as needed. |  |  |  |  | Customer
h. Devices
Overview: ELD Tablets are automatically added to the device page when they are installed and provisioned. The Vehicle IDs within the HOS portal can only be changed from the tablet during provisioning or re-provisioning.
| Provide training and overview on Devices. See training topics below. |  |  |  | https://help.gpsinsight.com/docs/about-hours-of-service/administrator-reference/hos-admin-setup-tasks/ | Account Manager, Customer
| Add Asset manually and via import. |  |  |  |  | Customer
| Edit/Delete an Asset. |  |  |  |  | Customer
| Provide training and overview on how to create a new Asset Group. |  |  |  |  | Customer
i. Assets & Asset Groups
Overview: Optional setting that enables filtering in reports. This is helpful for Users who are responsible for more than one terminal.
| Provide training and overview on Assets. See training topics below. |  |  |  | https://help.gpsinsight.com/docs/about-hours-of-service/administrator-reference/hos-admin-setup-tasks/ | Account Manager, Customer
| Add Asset manually and via import. |  |  |  |  | Customer
| Edit/Delete an Asset. |  |  |  |  | Customer
| Provide training and overview on how to create a new Asset Group. |  |  |  |  | Customer
j. Locations
Overview: Optional setting that enables Landmark names to be displayed in addition to standard location data on reports and on Driver logs. Recommend exporting lat/long from existing GIS tool or GPS Insight then importing into HOS Portal.
| Provide training and an overview of Locations to Customer. |  |  |  | https://help.gpsinsight.com/docs/about-hours-of-service/administrator-reference/hos-admin-setup-tasks/ | Account Manager, Customer
| Add Location (Landmark) manually and via import. Lat/Long needed. |  |  |  |  | Customer
k. DVIR
Overview: Configure and Customize DVIR Inspection Checklist.
| Provide an overview of DVIR to Customer. |  |  |  |  | Account Manager, Customer
| Account Manager to send links to Customer regarding DVIR to distribute to Drivers. |  |  |  | https://help.gpsinsight.com/docs/about-hours-of-service/driver-reference/completing-a-roadside-inspection/ | Account Manager, Customer
| Configure/Customize DVIR Checklist for both Vehicles and Assets. Add a New Part and Defect. |  |  |  |  | Customer
| Add a new Inspection report (create a failed DVIR from Tablet during the sign out process). |  |  |  |  | Customer
| Correct a failed DVIR from the HOS Portal. |  |  |  |  | Customer
l. HOS Reports in GPSI Hours of Service Portal
Overview: Customer should review their HOS portal and logs every day. This information is accessible through the GPSI Fleet Tracking Portal and HOS Portal. This process should usually take place at the beginning of Customer drivers’ day. Initially after implementation, Customer may want to do this process several times a day. Remember, during the initial implementation, Customer drivers are required to continue to use paper logs until Customer feel confident in their ability to correctly use the system everyday.
| Provide an overview of HOS Reports, including DVIR, available through the GSPI Hours of Service Portal. Reports will be manually ran daily by Customer. |  |  |  |  | Account Manager, Customer
| Verify data looks correct by checking for driving events, off duty events, location data, mileage data, shipping information, trailer information and proper sign out by Drivers. |  |  |  |  | Customer
| Review filtering by driver, vehicle, groups and dates. |  |  |  |  | Customer
| Review editing of logs. |  |  |  |  | Customer
| Review Violation Reports. |  |  |  |  | Customer
m. HOS in GPSI Fleet Tracking Portal
Overview: Some administrative tasks that Customer can perform within the ISE application for HOS setup are now available from the GPS Insight HOS Integration Configuration page. This integration allows Customer to manage parts of the HOS setup process from within one place (e.g., adding ISE drivers and associating them to GPS driver profiles).
| Provide an overview of HOS in GPSI Portal to Customer, including; Dashboard recommendations, Dashlet configurations, HOS Driving Availability, and Driver-Vehicle Inspection Reports. |  |  |  |  | Account Manager, Customer
| Create HOS Dashboard. Add HOS Dashlets to it. Edit HOS Dashlets. |  |  |  |  | Customer
| Review HOS Driving Availability and Driver-Vehicle Inspection Reports. |  |  |  |  | Account Manager, Customer
| Provide an overview of HOS Integration Configuration options in GPSI Portal. More>Hours of Servicer>HOS Integration Configuration. A minimum of one Driver must be defined in the HOS Portal in order for the Configuration page to populate. |  |  |  |  | Account Manager, Customer
| Review HOS Integration Configuration and verify drivers are linked. Driver Ref ID in GPSI Portal must match Driver ID in HOS Portal in order to link. |  |  |  | https://help.gpsinsight.com/docs/about-hours-of-service/administrator-reference/configuring-hos-integration/ | Account Manager, Customer
| Review HOS Integration Configuration and verify vehicles are linked. Vehicle label in GPSI Portal must match Device ID in HOS Portal in order to link. |  |  |  | https://help.gpsinsight.com/docs/about-hours-of-service/administrator-reference/configuring-hos-integration/ | Account Manager, Customer
| Verify HOS Configuration Options are correct (Auto-Assign Driver on DVIR Accept checked. UnAssign Driver before Auto- Assigning checked). Slip seating make sure all 3 boxes are checked. |  |  |  | https://help.gpsinsight.com/docs/about-hours-of-service/administrator-reference/configuring-hos-integration/ | Account Manager, Customer
| Add new ISE Driver. |  |  |  |  | Customer
Status | 7. HOS Rules and Regulations Compliance Tools | Due Date | Date Scheduled | Date Completed | Tools | Resources
Overview: Customer should review their HOS portal and logs every day for compliance. This information is accessible through the GPSI Fleet Tracking Portal and HOS Portal. This process should usually take place at the beginning of Customer drivers’ day. Initially after implementation, Customer may want to do this process several times a day.
| Account Manager to provide overview regarding Compliance Tools available. Send Links to About Hours of service, Resolving Conflicts, Daily HOS Management Tasks, Daily Management Tasks. |  |  |  | https://help.gpsinsight.com/docs/about-hours-of-service/administrator-reference/daily-hos-management/ | Account Manager
| Customer should Resolve ALL Conflicts on the Home Screen EVERY DAY. Conflicts are critical because they prevent Customer drivers from being able to download any updated log data, which could create unwanted compliance issues during roadside inspections. Driver will be unable to download data if there are any conflicts. |  |  |  | https://help.gpsinsight.com/docs/about-hours-of-service/administrator-reference/resolving-conflicts/ | Customer
| Manage Unknown Driver Events ASAP. Customer to contact Driver of Vehicle and request Driver signs into ELD Tablet ASAP. |  |  |  | https://help.gpsinsight.com/docs/about-hours-of-service/administrator-reference/resolving-conflicts/ | Customer
| Manage Missing Location Conflicts ASAP. Driver should contact GPSI HOS Support immediately for assistance. |  |  |  | https://help.gpsinsight.com/docs/about-hours-of-service/administrator-reference/resolving-conflicts/#cmd_device_toc_575_1 | Customer
| The HOS Admin portal includes several reports that Customer can run at any time. At a minimum, we recommend that Customer regularly review the most common of these reports (Violation, Inspection, Log Edits) to ensure compliance with HOS regulations. The frequency with which Customer perform these tasks is up to Customers organization; we recommend that they become part of Customer daily/weekly workflow. |  |  |  |  | Customer
Status | 8. Training | Due Date | Date Scheduled | Date Completed | Tools | Resources
| The GPS Insight implementation team works with the Customer to define and develop a master software training schedule and identify the training participants who will learn how to use the GPS Insight web portal (admin user). A training program protocol must be established for Users and Drivers which requires them to take the online training courses to familiarize them with the new ELD requirements and process. |  |  |  |  | Account Manager
| Self-Paced Training: GPS Insight also offers self-paced, online training courses that participants can take on their own time. Using recorded videos and a multiple-choice/interactive quiz, learners can assess how well they meet course objectives. No registration is required. Access the courses from the Help Center. |  |  |  |  | Customer
| Live WebEx User special topic training sessions as needed. |  |  |  |  | Account Manager, Customer
a. Administrator and Manager
| Administrator Training: The initial session typically begins at the administrative level and account setup in line with Implementation plan via live WebEx. |  |  |  |  | Account Manager, Customer
Train Manager on Driver Training and ELD adoption resources.
| Manager Administrator Training: Additional training for administrative users occurs on dates suggested by the Customer. WebEx meetings can be recorded for playback for any individuals who are unable to attend. |  |  |  |  | Account Manager, Customer
b. Driver
| Driver Training: It is VERY important that every Driver who will be subject to HOS is trained on the new HOS system. Customer is responsible for ensuring their Drivers are trained. A designated Customer Driver Trainer is recommended to train Drivers and for tracking Driver training status. GPS Insight provides extensive online Self-Paced Training (Driver In-Cab + HOS Portal + DVIR) that participants can take on their own time. Using recorded videos and a multiple-choice/interactive quiz, learners can assess how well they meet course objectives. No registration is required. Access the courses from the Help Center. In addition to the training courses, the primary customer contact for the HOS system may find the Best Practice worksheet helpful, particularly if transitioning from a paper log system to an automated system. |  |  |  |  | Drivers
| Drivers also need to be trained on web portal functionality if they will also be a user in the application and have the ability to edit logs online. |  |  |  |  | Customer
| Process recommendations where multiple drivers can operate one vehicle: 1. Train customer HOS Manager 2. Train customer HOS Manager on driver procedures and help them come up with their own SOP on how and what the drivers are required to do 3. Customer HOS Manager then conducts training with their drivers and has them complete the online HOS Driver test 4. After all drivers pass the test the installer fully installs the GPS unit and Tablet making sure they verify unit/tablet operation with GPSI Support 5. Drivers begin using HOS immediately |  |  |  | https://help.gpsinsight.com/best-practice/promoting-driver-adoption-of-gps-tracking/ | Account Manager
| Process recommendations where one driver is always in the same vehicle: 1. Train customer HOS Manager 2. Fully install the GPS unit and Tablet, verify with TS, and then disconnect the power cable from the power dock 3. Train customer HOS Manager on driver procedures and help them come up with their own SOP on how and what the drivers are required to do 4. Customer HOS Manager then conducts training with their drivers and has them complete the online HOS Driver test 5. If driver passes the test and understands the HOS Managers tablet usage procedures, HOS Manager instructs driver to connect tablet |  |  |  | https://help.gpsinsight.com/best-practice/promoting-driver-adoption-of-gps-tracking/ | Account Manager
c. User
| User Training: GPS Insight provides an initial remote (WebEx) product training session(s) for users. Recommend setting up a reoccurring training meeting until all users are trained. |  |  |  |  | Users
Status | 9. Account Management | Due Date | Date Scheduled | Date Completed | Tools | Resources
Overview: We will help with ensuring Customer's achieve maximum ROI with our solution. That includes training, support assistance and quarterly account reviews. We understand Customer goals and show them creative ways to use the platform to affect positive change across their organization. Below are considerations and best practices:
a. Project Updates
| GPS Insight Account Manager will provide customer with biweekly updates during the implementation regarding the implementation progress. This update will include installation, account set up, integration, and training status. |  |  |  |  | Account Manager
a. Customer Meetings
| Provide Customer with an example of a quarterly account review and inquire as to what they would like to see in their account review. Include ELD Safety website statistics in Account Review. |  |  |  |  | Account Manager
| Determine who should attend account reviews with Customer. Recommend all upper management, department heads attend. |  |  |  |  | Account Manager
| Provide a quarterly account review 2 or 4 times a year. |  |  |  |  | Account Manager
| Show New Feature section in Help Center and include in user training meeting. Set a schedule for communicating New Features to Customer. |  |  |  |  | Account Manager
| Determine travel schedule for visits to Customer site. |  |  |  |  | Account Manager
c. Device Health
| Determine communication path for any device issues or system questions/requests. Recommend all device questions are sent to support via email with Account Manager cc'd, and all System related questions are sent/called into Account Manager. Determine if Customer would like to be cc'd on all Support cases. |  |  |  |  | Account Manager
| Provide Customer with Device Health Analysis at least twice a year. |  |  |  |  | Account Manager
| Show Customer how to perform their own Device Health Analysis using the Performance Report. |  |  |  |  | Account Manager

## Project Summary Report
GPS Insight Implementation Project Summary Report
|  |  | Customer Name: | 0
[5 empty] | Start Date: | 0
[5 empty] | End Date: | 0
Area | Tasks to Complete | % Complete | Not Started | Complete | In Progress | N/A
1. Contract & Account Creation | 11 | 0% | 11 | 0 | 0 | 0
2. Project Initiation | 26 | 0% | 26 | 0 | 0 | 0
3. Pre-Order (Applies to Paid Install Only) | 8 | 0% | 8 | 0 | 0 | 0
4. Order | 8 | 0% | 8 | 0 | 0 | 0
5. Installation | 16 | 0% | 16 | 0 | 0 | 0
6. Account Set Up | 68 | 0% | 67 | 0 | 0 | 0
7. HOS Rules and Regulations Compliance Tools | 5 | 0% | 6 | 0 | 0 | 0
8. Training | 11 | 0% | 11 | 0 | 0 | 0
9. Account Management | 8 | 0% | 8 | 0 | 0 | 0
Total: | 161 | 0% | 161 | 0 | 0 | 0